## Sheet2
Tasks | Start Date | End Date | Days | Status
Project Initiation | 01-22-2024 | 01-25-2024 | 4 | Completed
Aim and Objective Development | 01-26-2024 | 01-29-2024 | 4 | Completed
Research Proposal | 01-30-2024 | 2024-02-02 | 3 | Completed
Literature Review | 2024-03-02 | 2024-08-02 | 6 | Completed
Research stock data | 2024-09-02 | 2024-11-02 | 3 | Completed
Dataset Collection | 2024-12-02 | 02-14-2021 | 3 | Completed
DPP | 02-15-2024 | 02-18-2024 | 7 | Completed
Research Machine Learning Algorithms | 02-19-2024 | 02-28-2024 | 10 | Completed
Data Preprocessing | 02-29-2024 | 2024-07-03 | 8 | Completed
IPR | 2024-08-03 | 2024-10-03 | 3 | Completed
Analyze Stock Data | 2024-11-03 | 03-15-2024 | 5 | Completed
Design Machine Learning Models | 03-16-2024 | 03-24-2024 | 9 | Completed
Model training | 03-25-2024 | 03-29-2024 | 5 | Completed
Evaluating and optimize the stock price data | 03-30-2024 | 2024-08-04 | 8 | Completed
Evaluation of the Applied model | 2024-09-04 | 2024-12-04 | 4 | Completed
Review the model | 04-13-2024 | 04-14-2024 | 3 | Completed
Write Thesis | 04-15-2024 | 04-22-2024 | 8 | Completed
Review the document and final submission | 04-23-2024 | 04-28-2024 | 8 | Completed