## Sheet1
Task Number | Tasks | Start Date | End Date | Status
Task 1 | Projet Initiantion | 12/15/23 | 12/19/23 | Completed
Task 2 | Research Proposal | 12/20/23 | 12/22/23 | Completed
Task 3 | Aim and objective Development | 12/25/23 | 12/29/23 | Completed
Task 4 | Literature Review | 2024-01-01 | 2024-09-01 | Completed
Task 5 | Research design | 2024-10-01 | 2024-12-01 | Completed
Task 6 | Research Strategy | 01/15/24 | 01/18/24 | Completed
Task 7 | Research stock data | 01/19/24 | 01/31/24 | Completed
Task 8 | Research Machine Learning Algorithms | 2024-01-02 | 2/14/24 | Completed
Task 9 | Dataset Collections | 2/15/24 | 2/23/24 | Completed
Task 10 | Analyze Stock data | 2/26/24 | 2024-05-03 | Completed
Task 11 | Design Machine Learning Models | 2024-06-03 | 03/13/24 | Completed
Task 12 | Model training | 3/14/24 | 3/20/24 | Completed
Task 13 | Evaluating and Optimize the stock price data | 3/21/24 | 3/29/24 | Completed
Task 14 | Evaluation of the Applied model | 2024-01-04 | 2024-08-04 | Completed
Task 15 | Review the model | 2024-09-04 | 2024-01-04 | Completed
Task 16 | Write Thesis | 2024-12-04 | 4/22/24
Task 17 | Discussion | 4/23/24 | 4/28/24
Review the document and final submission